## Sheet1
Sprint Goal & Number	User Story ID	User Story	Tasks for User Story	Type	Story Points	Points Completed	Team Names/Contribution	Extra Details
2,3,4,5	2	As someone who plays board games offline, I would like to be able to play 2 players on the same device, so I can play with my relatives who don’t have their own tablet.	Overall: Enable 2 player local mode	gameplay	7 total	6
			Recognize "4-in-a-row" win conditions		2	2	Austin, Spencer	win conditions now recognized
			Represent 4x4 board and pieces via Unity		2	1		now displays win screen
			Enable placing of pieces on 4x4 board via drag and drop		3	3	Austin, Spencer	drag and drop functionality smoother

5	6	As a motor impaired user, I would like a click and place option, so that I am not locked out of playing by dragging mechanics I am unable to use.	Overall: enable click, drag, place	gameplay	4 total	3 total
			enable basic movement of pieces using mouse			2	Austin, Spencer	basic drag and drop functionality complete
			enable click to select and click to drop functionality			1		click and move mouse to move piece not yet complete, but has been started

4	7	As someone with tremors, I would like a click and hold option, so that when I shake I do not misclick pieces or places.	Overall Enable click and hold, drag, place	gameplay	4 total	4 total
			enable basic movement of pieces using mouse			2	Spencer	basic drag and drop functionality complete
			enable click and hold and move mouse to move pieces			2		click and hold now works for moving pieces