## Sheet1
Sprint Goal & Number | User Story | Type | Story Points | Points Completed | Team Names/Contribution | Extra Details
0 | Project Description | Doc. | 4 | 4 | Alex-4
0 | User Stories | Doc. | 4 | 4 | Forrest-4
1 | Complete SRS document | Doc. | 10 | 9 | Forrest-4, Alex-4, Peter-1
1 | Revise project description | Doc. | 2 | 2 | Alex-2
1 | Set up Zen Hub board | Doc. | 2 | 2 | Spencer-2
1 | Create Product backlog | Doc. | 4 | 2 | Austin-1, Forrest-1
1 | Create Sprint backlog | Doc. | 4 | 2 | Spencer-2
1 | Create source file for code | Dev. | 2 | 2 | Spencer-2
2 | Finish/update Product backlog | Doc. | 4 | 4 | Forrest - 4
2 | Finish/update Sprint backlog | Doc. | 4 | 4 | Forrest - 4
2 | Update SRS based on feedback | Doc. | 4 | 0
2 | Create mockup | Doc. | 5 | 0
2 | Create Use Case Models | Doc. | 10 | 0
2 | Create Readme File | Doc. | 5 | 0
2 | Begin board development | Dev. | 5 | 0 |  | Create a board that lists available pieces in text format and allows placement. T or S, D or L, H or S, C or S - TDHC is a tall dark hollow circle
2 | Sprint Review 2 | Doc. | 3 | 0
3 | Update product backlog | Doc. | 2
3 | Update sprint backlog | Doc. | 2
3 | Update SRS based on feedback | Doc. | 2
3 | Update Use Case Models | Doc. | 4
3 | Create Sequence Diagram | Doc. | 10
3 | User Story #2 | Dev. | 7 |  |  | As someone who plays board games offline, I would like to be able to play 2 players on the same device, so I can play with my relatives who don’t have their own tablet.
3 | User Story #17 | Dev. | 7 |  |  | As a new player, I would like an option to practice against basic ai, so that I can slowly increase my skill.
3 | Update Readme | Doc. | 4
3 | Sprint Review 3 | Doc. | 3
4 | Update Product and Sprint backlog | Doc. | 4
4 | Update SRS if needed | Doc. | 2
4 | Update Use Case Models | Doc. | 2
4 | Update Sequence Diagram | Doc. | 4
4 | Create Configuration Management Plan | Doc. | 4
4 | Create Domain Model Doc | Doc. | 6
4 | Create Focus Group Doc | Doc. | 4
4 | User Story #3 | Dev. | 10 |  |  | As someone who doesn’t have friends that play, I would like to have a matchmaking system, so I can play with people around the world.
4 | User Story #12 | Dev. | 7 |  |  | As a variety loving user, I would like multiple gameplay modes, so that I won't get bored of just one.
4 | Update Readme | Doc. | 4
4 | Sprint Review 4 | Doc. | 3
5 | Update Product and Sprint backlog | Doc. | 4
5 | Update SRS, Use Case, Sequence Diagram | Doc. | 2
5 | Update Domain Model | Doc. | 4
5 | Update Configuration Mgmt Plan | Doc. | 2
5 | Create Architecture Design Doc | Doc. | 5
5 | Create Detailed Design Doc | Doc. | 6
5 | User Story #4 | Dev. | 3 |  |  | As a colorblind user, I would like to have different color/indication options, so that I will be able to play with my handicap.
5 | User Story #6 | Dev. | 4 |  |  | As a motor impaired user, I would like a click and place option, so that I am not locked out of playing by dragging mechanics I am unable to use.
5 | User Story #14 | Dev. | 8 |  |  | As a potential new user, I would like a built in tutorial, so that I can learn the game without having to look up a guide.
5 | Update Readme | Doc. | 4
5 | Sprint Review 5 | Doc. | 3
6 | Finalize Product and Sprint backlog | Doc. | 2
6 | Finalize SRS | Doc. | 2
6 | Finalize Use Case | Doc. | 2
6 | Finalize Sequence Diagram | Doc. | 2
6 | Fnalize Domain Model | Doc. | 2
6 | Finalize Configuration Mgmt Plan | Doc. | 2
6 | Finalize Architecture Design | Doc. | 2
6 | Finalize Detailed Design | Doc. | 2
6 | Create remaining tasks and future plan | Doc. | 2
6 | Finalize Readme | Doc. | 2
6 | User Story #5 | Dev. | 6 |  |  | As a visually impaired user, I would like to have a read-aloud option, so that I can be sure I’m picking the right piece.
6 | User Story #7 | Dev. | 4 |  |  | As someone with tremors, I would like a click and hold option, so that when I shake I do not misclick pieces or places.
6 | User Story #10 | Dev. | 4 |  |  | As a slow player, I would like an option to save my current game, so that I can think about my turn overnight.
6 | Sprint Review 6 | Doc. | 3
7 | User Story #13 | Dev. | 10 |  |  | As a competitive user, I would like a ranked option, so that I can play against opponents of similar skill.
7 | User Story #18 | Dev. | 7 |  |  | As a puzzle lover, I would like an option where the player has a preset board and has to decide the best move, so that I can test my knowledge of the game.
7 | User Story #20 | Dev. | 10 |  |  | As someone with low system specs, I would like a low-power/low-graphics mode, so that I can play the game without constant freezing.
7 | User Story #23 | Dev. | 8 |  |  | As a new player, I would like to see a hint system, so as I play I learn new tips about how to play.
8 | User Story #16 | Dev. | 6 |  |  | As someone who uses a lot of social media, I would like an option to post screenshots of my games, so that I can share interesting moments with all my friends.
8 | User Story #19 | Dev. | 4 |  |  | As a multitasking user, I would like a notification system that tells me when a move is made, so that I know when it is my turn to go.
8 | User Story #21 | Dev. | 7 |  |  | As a speedrunner, I would like a timed option, so that I can ensure my games are always lightning fast.
8 | User Story #22 | Dev. | 8 |  |  | As a completionist, I would like achievements in the game, so I can try to hunt down every trophy-worthy scenario.
9 | User Story #8 | Dev. | 8 |  |  | As someone who mostly plays online, I would like a chat option, so that I can make new friends while playing the game.
9 | User Story #9 | Dev. | 4 |  |  | As a parent, I would like the option to disable chat, so that my child does not get into dangerous situations online.
9 | User Story #24 | Dev. | 6 |  |  | As a player who loves stats, I would like to see a stat page, so that I can see how many wins and losses I have.
9 | User Story #25 | Dev. | 7 |  |  | As a parent, I would like to have a chat filter option, so that my child does not need to read curse words online.
9 | User Story #26 | Dev. | 7 |  |  | As a competitive player, I would like to be able to send my opponents emotes, so they know how badly they are being beaten.
10 | User Story #1 | Dev. | 3 |  |  | As someone who likes bright and colorful games, I would like to be able to choose the style/color of my pieces and board, so that my board never gets boring.
10 | User Story #11 | Dev. | 10 |  |  | As a pro player, I would like an analysis system to measure the effectiveness of my turns, so that I can improve and expand on my abilities.
10 | User Story #15 | Dev. | 3 |  |  | As someone who wants to support the dev team, I would like an option to buy an ad free version, so I can be rewarded for my support.
10 | User Story #27 | Dev. | 7 |  |  | As a competitive player, I would like a live coaching option, so that professionals can help me improve my play.