## Sheet1
Sprint Goal & Number	User Story ID	User Story	Tasks for User Story	Type	Story Points	Points Completed	Team Names/Contribution	Extra Details

6	12	As a variety loving user, I would like multiple gameplay modes, so that I won't get bored of just one.	Overall: Enable multiple modes	gameplay	9 total	3 total
			Create Casual Mode via Unity		3	1	Austin, Spencer	turn based play now works as it should
			Create Competitive mode via Unity		3	1	Austin, Spencer	turn based play now works as it should
			Create vs. AI Mode via Unity		3	1	Austin, Spencer	turn based play now works as it should
6	13	As a competitive user, I would like a ranked option, so that I can play against opponents of similar skill.	Overall: Match scores with opponent	gameplay	6 total	2 total
			Enable 2 player basic game		2	2	Austin, Spencer	turn based play now works as it should, executable created
			record score		2	0
			match score with future opponent		2	0