## Sheet1
ID	User Stories	Sprint #	Story Priority	Story Status	Story points
						Categories of Priority
1	As someone who likes bright and colorful games, I would like to be able to choose the style/color of my pieces and board, so that my board never gets boring.	10	5	Not started	3	1 = Most important functionality
2	As someone who plays board games offline, I would like to be able to play 2 players on the same device, so I can play with my relatives who don’t have their own tablet.	2,3,4,5	1	Finished	7	2 = Important functionality
3	As someone who doesn’t have friends that play, I would like to have a matchmaking system, so I can play with people around the world.	7	2	Not started	10	3 = Desired functionality
4	As a colorblind user, I would like to have different color/indication options, so that I will be able to play with my handicap.	7	3	Not started	3	4 = Optional functionality
5	As a visually impaired user, I would like to have a read-aloud option, so that I can be sure I’m picking the right piece.	7	4	Not started	6	5 = Extended functionality
6	As a motor impaired user, I would like a click and place option, so that I am not locked out of playing by dragging mechanics I am unable to use.	4	3	Finished	4
7	As someone with tremors, I would like a click and hold option, so that when I shake I do not misclick pieces or places.	4	4	Finished	4
8	As someone who mostly plays online, I would like a chat option, so that I can make new friends while playing the game.	9	5	Not started	8
9	As a parent, I would like the option to disable chat, so that my child does not get into dangerous situations online.	9	5	Not started	4
10	As a slow player, I would like an option to save my current game, so that I can think about my turn overnight.	7	4	Not started	4
11	As a pro player, I would like an analysis system to measure the effectiveness of my turns, so that I can improve and expand on my abilities.	10	5	Not started	10
12	As a variety loving user, I would like multiple gameplay modes, so that I won't get bored of just one.	6	2	In progress	7
13	As a competitive user, I would like a ranked option, so that I can play against opponents of similar skill.	6	4	In progress	10
14	As a potential new user, I would like a built in tutorial, so that I can learn the game without having to look up a guide.	7	2	Not started	8
15	As someone who wants to support the dev team, I would like an option to buy an ad free version, so I can be rewarded for my support.	10	5	Not started	7
16	As someone who uses a lot of social media, I would like an option to post screenshots of my games, so that I can share interesting moments with all my friends.	9	5	Not started	6
17	As a new player, I would like an option to practice against basic ai, so that I can slowly increase my skill.	3,7	2	In progress	7
18	As a puzzle lover, I would like an option where the player has a preset board and has to decide the best move, so that I can test my knowledge of the game.	7	3	Not started	7
19	As a multitasking user, I would like a notification system that tells me when a move is made, so that I know when it is my turn to go.	8	4	Not started	4
20	As someone with low system specs, I would like a low-power/low-graphics mode, so that I can play the game without constant freezing.	7	4	Not started	10
21	As a speedrunner, I would like a timed option, so that I can ensure my games are always lightning fast.	8	4	Not started	7
22	As a completionist, I would like achievements in the game, so I can try to hunt down every trophy-worthy scenario.	9	5	Not started	8
23	As a new player, I would like to see a hint system, so as I play I learn new tips about how to play.	7	3	Not started	8
24	As a player who loves stats, I would like to see a stat page, so that I can see how many wins and losses I have.	9	4	Not started	6
25	As a parent, I would like to have a chat filter option, so that my child does not need to read curse words online.	10	5	Not started	7
26	As a competitive player, I would like to be able to send my opponents emotes, so they know how badly they are being beaten.	9	5	Not started	7
27	As a competitive player, I would like a live coaching option, so that professionals can help me improve my play.	10	5	Not started	10