## Sheet1
Sprint Goal & Number | User Story ID | User Story | Tasks for User Story | Type | Story Points | Points Completed | Team Names/Contribution | Extra Details
2 | 2 | As someone who plays board games offline, I would like to be able to play 2 players on the same device, so I can play with my relatives who don’t have their own tablet. | Overall: Enable 2 player local mode | Gameplay | 7 total | 4
|  |  | Recognize "4-in-a-row" win conditions |  | 2 | 0 |  | Initial drag and drop mechanics tested. Game mechanics pushed back.
|  |  | Represent 4x4 board and pieces via Unity |  | 2 | 2 | Austin/Spencer
|  |  | Enable placing of pieces on 4x4 board via drag and drop |  | 3 | 2 | Austin/Spencer | Pieces drag, but do not place on board.