## Sheet1
ID | User Stories | Sprint # | Story Priority | Story Status | Story points
Categories of Priority
1 | As someone who likes bright and colorful games, I would like to be able to choose the style/color of my pieces and board, so that my board never gets boring. | 8 | 5 | Not started | 3 | 1 = Most important functionality
2 | As someone who plays board games offline, I would like to be able to play 2 players on the same device, so I can play with my relatives who don’t have their own tablet. | 2 | 1 | In progress | 7 | 2 = Important functionality
2 | As someone who doesn’t have friends that play, I would like to have a matchmaking system, so I can play with people around the world. | 3 | 2 | Not started | 10 | 3 = Desired functionality
3 | As a colorblind user, I would like to have different color/indication options, so that I will be able to play with my handicap. | 4 | 3 | Not started | 3 | 4 = Optional functionality
4 | As a visually impaired user, I would like to have a read-aloud option, so that I can be sure I’m picking the right piece. | 5 | 4 | Not started | 6 | 5 = Extended functionality
5 | As a motor impaired user, I would like a click and place option, so that I am not locked out of playing by dragging mechanics I am unable to use. | 4 | 3 | Not started | 4
6 | As someone with tremors, I would like a click and hold option, so that when I shake I do not misclick pieces or places. | 5 | 4 | Not started | 4
7 | As someone who mostly plays online, I would like a chat option, so that I can make new friends while playing the game. | 7 | 5 | Not started | 8
8 | As a parent, I would like the option to disable chat, so that my child does not get into dangerous situations online. | 7 | 5 | Not started | 4
9 | As a slow player, I would like an option to save my current game, so that I can think about my turn overnight. | 5 | 4 | Not started | 4
10 | As a pro player, I would like an analysis system to measure the effectiveness of my turns, so that I can improve and expand on my abilities. | 8 | 5 | Not started | 10
11 | As a variety loving user, I would like multiple gameplay modes, so that I won't get bored of just one. | 3 | 2 | Not started | 7
12 | As a competitive user, I would like a ranked option, so that I can play against opponents of similar skill. | 6 | 4 | Not started | 10
13 | As a potential new user, I would like some sort of built in tutorial, so that I can learn the game without having to look up a guide. | 4 | 2 | Not started | 8
14 | As someone who wants to support the dev team, I would like an option to buy an ad free version, so I can be rewarded for my support. | 8 | 5 | Not started | 7
15 | As someone who uses a lot of social media, I would like an option to post screenshots of my games, so that I can share interesting moments with all my friends. | 7 | 5 | Not started | 6
16 | As a new player, I would like an option to practice against basic ai, so that I can slowly increase my skill. | 2 | 2 | Not started | 7
17 | As a puzzle lover, I would like an option where the player has a preset board and has to decide the best move, so that I can test my knowledge of the game. | 5 | 3 | Not started | 7
18 | As a multitasking user, I would like a notification system that tells me when a move is made, so that I know when it is my turn to go. | 5 | 4 | Not started | 4
19 | As someone with low system specs, I would like a low-power/low-graphics mode, so that I can play the game without constant freezing. | 6 | 4 | Not started | 10
20 | As a speedrunner, I would like a timed option, so that I can ensure my games are always lightning fast. | 6 | 4 | Not started | 7
21 | As a completionist, I would like achievements in the game, so I can try to hunt down every trophy-worthy scenario. | 7 | 5 | Not started | 8
22 | As a new player, I would like to see a hint system, so as I play I learn new tips about how to play. | 5 | 3 | Not started | 8
23 | As a player who loves stats, I would like to see a stat page, so that I can see how many wins and losses I have. | 7 | 4 | Not started | 6
24 | As a parent, I would like to have a chat filter option, so that my child does not need to read curse words online. | 7 | 5 | Not started | 7
25 | As a competitive player, I would like to be able to send my opponents emotes, so they know how badly they are being beaten. | 7 | 5 | Not started | 7
26 | As a competitive player, I would like a live coaching option, so that professionals can help me improve my play. | 8 | 5 | Not started | 10